## Sheet0
What Went Well | What Went Poorly | What Could Be Improved | Action Items for Next Sprint | Guidelines / Learnings
Successfully implemented NFC UID–based patient identification, allowing automatic retrieval of patient records. | Initial difficulties were faced while handling NFC hardware simulation and polling mechanisms. | Improve exception handling for NFC read/write failures and OCR errors. | Implement security measures such as data encryption for patient information. | Prioritize simplicity and reliability, especially for healthcare applications.
Developed a user-friendly Tkinter GUI suitable for healthcare use with clearly labeled input fields. | GUI responsiveness reduced slightly during background threads such as NFC polling and OCR processing | Optimize thread management to maintain smooth UI performance. | Improve OCR accuracy by adding image preprocessing techniques | Maintain clean, modular code to improve scalability and maintainability
Integrated SQLite database to store patient records, medication history, and email logs locally | Error handling was limited for missing files, invalid images, or OCR failures | Enhance the UI design using consistent spacing, colors, and accessibility guidelines | Add role-based access (doctor/admin) for better system control | Ensure data privacy and compliance with healthcare standards
Implemented OCR functionality to scan prescription images and extract text automatically | Managing multiple threads without affecting the UI required extra debugging and testing | Improve data validation for patient phone numbers, emails, and text fields. | Perform unit testing for database and NFC modules. | Always test features with real-world scenarios and edge cases
PDF generation and PDF preview feature worked as expected for patient health reports. | The UI design, though functional, could be improved to look more modern and consistent. | Add confirmation dialogs for delete actions in medication history | Redesign UI using a Figma-approved layout and apply consistent styling. | Maintain proper documentation for future enhancements
Successfully enabled emailing of patient reports with automatic logging in the database.
Multi-module integration (GUI, database, NFC simulation, OCR, email) worked together smoothly